Administrator’s Weekly Report  Economy

March 6-12, 2004

HIGHLIGHTS

--  As of March 10, 2004, estimated crude oil export revenue reached $2.8 billion for 2004.

--  $3.6 billion out of supplemental funds are currently committed to Iraq relief and reconstruction efforts, 35 percent of the July 1 goal.

I.  BUILD FINANCIAL MARKET STRUCTURES

Modernize the Central Bank; 	Commercial Banking System; Re-establish Baghdad Stock Exchange; Restructure National Debt

- From March 5-10, members of the Central Bank of Iraq, Central Statistical Organization (an organization within the Iraqi Ministry of Planning) and CPA-Economic Policy visited Mosul, Arbil, and Sulaymaniyah to arrange for cooperation in the gathering and reporting of macro-economic, fiscal, and money and banking statistics. The delegation met with the top managers of the Central Bank and local commercial bank branches, and the directors of the governorates’ statistical offices.  During the trip, the governorate ministers of finance pledged their support for the effort, and bankers in all three regions expressed their willingness to begin supplying weekly money supply statistics, including cash in vaults and deposits.

- Central Bank staff went to Beirut this week for continued training on the bank’s internal automation system, which was in the process of being implemented before the war and is now being reinstalled.  Information technology specialists from the Federal Reserve Bank of New York arrived this week to conduct a study of the Iraqi banking system’s IT, communications, and automation capabilities and needs, with a particular focus on the Central Bank.

- Staff and officials from the Central Bank and the Ministry of Finance, along with members of CPA Economic Policy and OMB, traveled to Beirut for meetings with the International Monetary Fund to discuss macroeconomic framework analysis.  Staff also attended meetings in Beirut with the Paris Club concerning Iraq’s foreign debt.

- The New Iraqi Dinar (NID) has been stable the past four weeks.  At the NID auction on March 11, the settlement price was 1,415 dinars per dollar.  The value of dollars sold at the auction varied over the week from $9.3 to $22 million.  The exchange rate on the Baghdad streets was 1,430 dinars per dollar on March 7.  During the past week, March 6-11, the NID appreciated 0.7 percent against the U.S. dollar.

Source: CPA Senior Advisor to the Central Bank of Iraq

Source: CPA Senior Advisor to the Central Bank of Iraq

- The annualized weekly volatility of the new Iraqi dinar this past week was 3.0 percent.

- CPA continues preparations for the Iraq Stock Exchange: training for stock exchange staff; renovations of the site; coordination for additional technical experts; meeting with the future Board of Directors; revising job descriptions for the department heads; and finishing equipment installation.  Five companies have met the listing standards thus far.  The Iraq Stock Exchange is expected to open in early April.

II.  DEVELOP TRANSPARENT BUDGETING AND ACCOUNTING ARRANGEMENTS

Redrafting and Execution of 2004 Budget

- As of March 11, the balance in the Development Fund for Iraq (DFI) was $8.1 billion, comprised of $6.9 billion in the original Federal Reserve Bank of New York (FRBNY) account, and $1.2 billion on deposit in DFI-Baghdad.  Of this, $5.4 billion is already committed to projects, and the remaining $2.7 billion is slated for projected 2004 budget items.  Since establishment, the DFI investment program at FRBNY earned $15 million in interest.  As of March 11, the total payments out of the DFI amounted to $5.6 billion.

- State Department and U.S. Agency for International Development (USAID) assistance to Iraq disbursed in FY 2003/2004 totals $2.6 billion as of March 12, 2004:

    - USAID/ Asia and Near East (ANE): 				$1.9 billion

    - USAID/ Office of Foreign Disaster Assistance (OFDA): 	$87 million

    - USAID/ Food for Peace (FFP): 					$426 million

    - USAID/ Office of Transition Initiatives (OTI): 			$104 million

    - State Department/ Bureau of Population, Refugees,

and Migration (PRM): 						$39 million

- The Program Management Office (PMO) intends to commit $10.4 billion (56 percent of the $18.4 billion supplemental) toward contracts by July 1, 2004.  $3.6 billion are currently committed to Iraq relief and reconstruction efforts, 35 percent of the July 1 goal.  Currently, $2.1 billion of funds are obligated with contractors (20 percent of the committed fund’s goal).  The following chart shows the money committed by sector for construction and non-construction projects as of March 12.

Source: CPA Program Management Office

Section 2207 of the Emergency Supplemental Appropriations Act for Defense and for the Reconstruction of Iraq and Afghanistan, FY 2004 (Public Law 108-106) enumerates the allotments granted to CPA for each sector and levies a quarterly reporting requirement to Congress detailing PMO’s spending.

III.  PRIVATE SECTOR INITIATIVES

Streamline existing commercial code/regulations; Facilitate lending to private businesses; Technical Assistance for Small and Medium Enterprises (SMEs); Iraqi Participation in Reconstruction Subcontracts; Business Development

- The Minister of Trade signed the company registration regulation, which streamlines procedures for registering domestic entities, and implements, in part, CPA Order No. 39 by providing procedures for the registration of Iraqi entities owned by foreign shareholders.

- Micro-lending in the Al-Anbar province suffers from a lack of participation because of threats to local bankers.

- The ‘road-show’ throughout Europe promoting foreign investment in Iraq has already yielded visits from several companies.  CPA posted information from the road show, including an investor packet, on the CPA internet website.

IV.  DESIGN OIL TRUST FUND

Proposal for Oil Trust Fund

- As of March 10, 2004, estimated crude oil export revenue reached $2.8 billion for 2004 (crude oil export revenue for 2003 [June - December] was $5.1 billion).

V.  LAY FOUNDATIONS FOR AN OPEN ECONOMY

Provide IG Staff Capability; Trade Bank; WTO Observer Status; Draft Intellectual Property law to IGC by April 15, 2004; Develop Framework for Collateralizing Movable and Immovable Property

- The Turkish and Iraqi Delegations met in Ankara on March 9 – 12 to discuss common concerns. The two neighbors recognized that economic cooperation provides the necessary stability for democracy and reform, and intend to continue developing their mutually beneficial trade and investment relations.  The two sides discussed the following:

  - The financial, operational and security issues of the Kirkuk-Yumurtalık pipeline. The Turkish side said that the Turkish domestic market and transportation of natural gas to Europe via Turkey constitutes the best option for Iraqi natural gas exports. Turkish companies BOTAŞ and TPAO expressed their willingness to develop five gas fields in Iraq, and TÜPRAŞ expressed its desire to purchase oil from SOMO at the Ceyhan Terminal.

  - A framework for processing the Border Trade Arrangement (of January 14 – 16, 2000) registered and funded contracts that were interrupted by the recent conflict.

  - Turkish intent to provide seasonal data on snowfall and reservoir levels sufficient for Iraq to develop its water plan for this year.

  - The Turkish draft Preferential Trade Agreement distributed among Iraqi ministries for comment; both sides are interested in discussing a mutually beneficial bilateral trade agreement that is consistent with the principles of the World Trade Organization.

- Recognition that the current border gate at Ibrahim Khalil-Habur is inadequate to support their growing bilateral trade, and that a second border crossing point would benefit both sides.

- As of March 14, the Trade Bank of Iraq has opened 109 letters of credit totaling $499 million covering imports from 24 countries, with an additional 20 letters of credit in the pipeline. In addition, there is one letter of credit to be issued under a U.S. Export-Import Bank guarantee, and six Oil for Food letters of credit are in process.

VI.  PURSUE NATIONAL STRATEGY FOR HUMAN RESOURCES DEVELOPMENT

Begin to employ workers in Public Works programs around the country

- The Ministry of Labor and Social Affairs (MoLSA) now has 15 employment centers open throughout the country, which have registered over 400,000 job seekers.  MoLSA is on target to have 28 centers nationwide open by June 30.  In addition, MoLSA began a campaign to reach out to international companies doing work in Iraq to hire registered Iraqi workers through the employment centers.

- Combined Joint Task Force 7 (CJTF-7) Civil Affairs units estimate that the CPA has created 379,721 jobs for Iraqi citizens (45 percent of the CJTF-7 target of 850,000):

    - Security/National Defense employs 				220,923

    - Regional Jobs Programs employ   				  37,421

    - CJTF-7 employs 							  51,673

    - Civilian contractors working under CPA contracts employ 	  68,154

    - Governorate Teams employ 					    1,550

VII. INITIATE PUBLIC SECTOR MANAGEMENT REFORM

Civil Service Salary Review

- As of March 11, the CPA Administrator had appointed Inspectors General (IG) in 14 Ministries, and another five Ministries had selected nominees (out of 26 total).  All current Ministries are expected to have IG appointed by the end of March.  CPA has now held two initial daylong seminars that were attended by a total of 12 IG and other Ministry and Board of Supreme Audit (BSA) representatives.  The seminars aimed to develop a shared understanding of what will be involved in implementing the IG concept in Iraq, including its linkages with the new Commission on Public Integrity and a revitalized BSA.