## A-Steam Power Stations
REPORT DATE - 03 FEBRUARY 2004
A - Steam Power Stations
Power Stations | Type Fuel | No. of Units | No. of Operating Units | Units Load (MW) | [5 empty] | Total Load MW | Target Load MW | Remarks
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6
Dibis | Natural Gas | 4 | 2 | Units Load (MW) 1: 9; Units Load (MW) 2: 9 | 18 | 24
Baiji | Fuel Oil | 6 | 1 | Units Load (MW) 1: 90 | 90 | 500 | #3 stopped - tripped by furn press high
Daura | Fuel Oil | 4 | 1 | Units Load (MW) 3: 70 | 70 | 180
South Baghdad | Fuel Oil | 6 | 1 | Units Load (MW) 6: 30 | 30 | 200
Mussaibe | Crude and Fuel Oil | 4 | 4 | 170 | 170 | 170 | 170 |  |  | 680 | 860 | #1 tripped by EHG with (200) MW
Nassirya | Crude | 4 | 3 | Units Load (MW) 1: 150; Units Load (MW) 3: 90; Units Load (MW) 4: 140 | 380 | 600 | #3 synchro at 515
Najebia | Natural Gas and Crude | 2 | 2 | Units Load (MW) 4: 90; Units Load (MW) 5: 85 | 175 | 160
Hartha | Natural Gas and Crude | 4 | 1 | Units Load (MW) 1: 80 | 80 | 300
| Out of Service for Unscheduled Maintanence |  |  | Units Load (MW) 6: Total: | 1523 | 2824
Out of Service for Program Maintanence/Rehab
No activity
Not Performing at Peak Performance

## B- Gas_C-Power Stations
Report Date - 03 FEBRUARY 2004
B- Gas Power Stations | [6 empty] | C -Hydro Power Stations
Power Stations | No. of Units | No. of Operating Units | Station Load | Target Load | Fuel Use | Remarks | Power Stations | No. of Units | No. of Operating Units | Station Load | Target Load | Discharge m3/Sec
Gas Pressure
Baiji | 2 | 0 | 0 | 125 | Gas Oil |  | Musil Dam Main | 4 | 4 | 580 | 600
Quds | 2 | 2 | 230 | 160 | Gas Oil | #1 emerg stop due to turb filters cleaning | Musil Dam reg | 4 | 4 | 37 | 60
Mosil | 12 | 9 | 142 | 150 |  | #3 emerg stop due to n. gas pressure low | Musil Pumping | 2 | 1 | 110 | 0
Dibis | 3 | 1 | 30 | 30 |  |  | Haditha Dam | 6 |  |  | 160
Old Mulla | 12 | 7 | 86 | 128 |  | #4 tripped by turb vibration | Samarra | 3 | 2 | 44 | 55
New Mulla | 6 | 3 | 105 | 173 |  |  | Himrin | 2 | 2 | 34 | 21
Taji | 7 | 4 | 69 | 55 |  |  | Hindia | 4 | 4 | 5 | 5
M. Taji | 2 | 1 | 8 | 18 |  |  | Kufa | 4 | 2 | 1 | 0
Daura | 4 | 2 | 50 | 30 |  |  |  |  | Total | 811 | 896
Hilla | 4 | 4 | 68 | 64 |  |  | System Generation |  |  | MWh
Najaf | 3 | 2 | 90 | 129 |  |  | Syrian Line Generation |  |  | MWh
Khor | 4 | 3 | 130 | 80 | Natural Gas |  | Turkey Line Generation |  |  | MWh
Shuaiba | 2 | 2 | 7 | 20 | Natural Gas |  | Total Generation |  | 87835 | MWh
M. Shuaiba | 2 |  |  |  | Natural Gas |  | System Peak Load |  | 3542 | MW
Petro | 4 | 1 | 42 | 0 | Natural Gas |  | Syria Peak Load |  | 60 | MW
M. Dibis | 4 | 0 | 0 | 24 | Natural Gas |  | Turkey Peak Load |  | 80 | MW
Mossil East | 5 | 3 | 18 | 0 | Gas Oil |  | Fixed Gen Peak Load |  | 266 | MW
Hmam/Zafranya | 7 | 3 | 45 |  | Gas Oil |  | Total Peak Load |  | 3928 | MW
Diesel |  |  |  |  | Gas Oil |  | Baghdad Load |  | 1470 | MW
|  | Total | 1120 | 1186
Notes: Prepared from data submitted by D.G. Mohsin T. Hassan (1 (914) 360 6590).
Edited by Electricity Commission U.S. Advisor Staff.

## Peak Loads
Report Date - 03 FEBRUARY 2004
GOVERNORATE | Peak Load MW | MWH | Average Load MW
Baghdad | 1470
Duhok | 80
Naynawa | 32
Tamim | 125
Salah Aldeen | 190
Anbar | 180
Dyala | 100
Babil | 95
Kirbala | 90
Najaf | 110
Kadsya | 65
Wasit | 95
Muthana | 60
Nasirya | 110
Misan | 55
Basra | 320
3470