Daily Power System Highlights for February 24, 2004

The CPA Electricity Advisor issues this report to note significant events or conditions of interest in the power sector.  The basic daily data on the power system is available on the CPA web site.

HIGHLIGHTS:   Najaf 1 and New Mulla 1 out of programmed maintenance and operational ahead of schedule.

Generation:

Peak Power 4011Mw, 88,490Mw hours, 7-day Avg. 4157Mw

Generators Returned to Service                                                                              223 Mw

Dibis 2, SP                                                                                                                         8 Mw

Baiji 1, CP                                                                                                                        85 Mw

New Mulla 1                                                                                                                     30 Mw

Khor Zubayr 4                                                                                                                  50 Mw

Najaf 2                                                                                                                              50 Mw

Generators Unscheduled Out of Service                                                         1043 Mw				  876 Mw

| PLANT | Type SP, CP, RP, HP | Fault | Mw |
| --- | --- | --- | --- |
| Dibis 4 | SP | Boiler Leak | 8 |
| * South Baghdad 4 | SP | Boiler Leak | 30 |
| South Baghdad 5 | SP | Boiler Leak | 30 |
| * South Baghdad 6 | SP | Boiler Leak | 30 |
| Hartha 4 | SP | Excit. problem | 150 |
| * Mussaibe 1 | SP | Boiler Leak | 200 |
| * Nassirya 3 | SP | Vacuum problems | 165 |
| Baiji 2, | CP | Lubricating oil leak | 110 |
| * Qudis 2 | CP | Fuel level low | 80 |
| Hilla 1 | CP | Cooling System problems | 20 |
| Hilla 2 | CP | Servo | 20 |
| Mosil 1 | CP | Rotor Defect | 15 |
| Mosil 9 | CP | Rotor Defect | 15 |
| * Mosil 7,8 | CP | Transistor problems | 30 |
| Old Mulla 1 | CP | Acc Gear | 15 |
| Old Mulla 2 | CP | Servo | 15 |
| New Mulla 2 | CP | Maintenance | 30 |
| New Mulla 6 | CP | Generator Defect | 30 |
| Taji 3, | CP | Compressor | 15 |
| Taji Mobile, 2 | CP | Software problem | 15 |
| * Doura 4 | CP | Circuit breaker | 20 |

* RED – Denotes out of service since last report

Generators Scheduled Out of Service                                                                                     831 	Mw

| PLANT | Type SP/NG | Prog. Maintenance(M) / Rehab (R) | Maint. Org. | Date out-of -service | Est. In-service Date | Mw |
| --- | --- | --- | --- | --- | --- | --- |
| Baiji 2 | SP | M | Bechtel | 2 Jan 04 | 4 Mar | 100 |
| Doura 2 | CP | M |  |  |  | 20 |
| Doura 3 | CP | R | GRD/RIE | 1 Mar 03 | 15 May | 20 |
| Doura 4 | SP | M | ME | 2 Feb 04 | 20 Apr | 65 |
| Doura 5 | SP | R | Bechtel | Jul 03 | 30 Apr | 100 |
| Doura 6 | SP | R | Bechtel | Jul 03 | 31May | 100 |
| Dibis 3 | SP | M | ME | 30Dec 03 | 31 May | 8 |
| Dibis 4 | CP | R | GRD/RIE | Sep 03 | 30 Mar | 18 |
| Khor Zubayr 2 | CP | M | ME | 19 Feb 04 | TBD | 50 |
| Mussaibe 4 | SP | M | ME | 7 Feb 04 | 7 Mar | 180 |
| New Mulla 2 | CP | M | ME | 17 Feb04 | TBD | 30 |
| Old Mulla 5 | CP | M | GRD/RIE | 1 Nov 03 | 15 May | 15 |
| Old Mulla 10 | CP | M | GRD/RIE | 6 Jan 04 | 15 May | 15 |
| Old Mulla 12 | CP | R | GRD/RIE | 1 Oct 03 | 15 May | 15 |
| Taji 7 | CP | R | GRD/RIE | 1 Oct 03 | TBD | 15 |
| Shuaiba 1 | CP | M | ME | 14 Feb 04 | 31 May | 20 |
| South Baghdad 1 | SP | M | ME | 12 Feb 04 | 12 Apr | 30 |
| South Baghdad 2 | SP | M | ME | 12 Feb 04 | 12 Apr | 30 |

LEGEND OF ELECTRICAL SYSTEM POWER SOURCE

SP:  STEAM POWER – These plants use either fuel oil or crude in burners

CP:  COMBUSTION POWER

RP:  RECIPROCATING POWER

HP:  HYDRO POWER

Transmission:

| LINE | Kv | Fault | Maint. Org. | Date out-of -service | Est. In-service Date | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Nassiriya-Khor Zubayr | 400 | Sabotage | Bechtel |  | 1 May | 102 towers complete/211req’d |
| Haditha-Baghd West | 400 | Sabotage | GRD/RIE |  | 20 Apr | 45 towers complete/236 req’d |
| Hartha-Qut – Wasit | 400 | Sabotage | GRD/RIE |  | 7 Mar | 281 towers complete/293 req’d |
| Baiji - Baghd West #1 | 400 | Sabotage | GRD/RIE |  | 14 Mar | 68 towers complete/68 req’d |
| Baghd E.-Baghd S. #2 | 400 | New Line | GRD/RIE |  | 28 Feb | 81 towers complete/81req’d |
| Baghd S. – Diwaniyah | 400 | Sabotage | GRD/RIE |  | Compl. 24 Jan | 27 towers complete/27 req’d |
| Haditha – Qaim | 400 | Sabotage | ME |  | TBD | No contract awarded |
| Baiji – Haditha | 400 | Sabotage | ME |  | TBD | No contract awarded |
| Diyala Connection | 400 | New Line | ME |  | 30 Apr |  |
| Dibis/Irbil-Quarqush | 132 | New Line | GRD/RIE |  | 15 May | Contractor on-site 20 Feb |
| Mosul – Mosul East | 132 | Sabotage | ME |  | TBD |  |
| Shuwaiba-Toba-Hamar | 132 | Sabotage | ME |  | 15 Feb/TBD | 43 towers complete/43 req’d |
| Baghd West – Jamia | 132 | Sabotage | ME |  | TBD |  |
| Omara-Burzegan | 132 | Looting | ME |  | 1 May | 26 towers complete/126 req’d |
| Temim- Tuz | 132 | Sabotage | ME |  | TBD |  |
| Nejibiya – Hartha | 132 | Sabotage | ME |  | TBD |  |

Lines Returned to service:

None reported today

Distribution:

| GOVERNORATE | Peak Load MW | MWH | Average Load MW |
| --- | --- | --- | --- |
| Power transferred from North to Middle 845 MW. |
| Power transferred from South to Middle 125 MW. |
| Baghdad | 1300 | 29740 | 1239 |
| Duhok | 84 | 1303 | 54 |
| Naynawa | 310 | 9447 | 394 |
| Tamim | 120 | 3827 | 159 |
| Salah Aldeen | 200 | 4837 | 202 |
| Anbar | 185 | 4012 | 167 |
| Dyala | 75 | 1847 | 77 |
| Babil | 75 | 2202 | 92 |
| Kirbala | 146 | 2657 | 111 |
| Najaf | 156 | 2861 | 119 |
| Kadsya | 55 | 1310 | 55 |
| Wasit | 65 | 1871 | 78 |
| Muthana | 59 | 1353 | 56 |
| Nasirya | 140 | 2807 | 117 |
| Misan | 61 | 1439 | 60 |
| Basra | 310 | 7455 | 311 |

Data compiled and reported by:

LTC Tharnell M. Thomas

CENTCOM LNO CPA  Ministry of Electricity

thomast2orha.centcom.mil